## Tasks and Timeline
Sauce & Spoon Project Plan
| Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
ID | [7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[8 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1: Selecte tablets and vendors
1.1 | Research and compare tablet system options. |  |  |  | 1 day | Seydou | bar: WEEK 1 M
1.2 | Connect Suace & Spoon with terrific Tablets for branding |  |  |  | 4 hours | Seydou | bar: WEEK 1 T
1.3 | Generate quotes and review costs for tablets and electrician vendors |  |  |  | 4 hours | Seydou | bar: WEEK 1 W
1.4 | Test tablet systems |  |  |  | 3 days | Peta | bar: WEEK 1 R to WEEK 2 M
1.5 | Choose a tablet operating system and order tablets |  |  |  | 2 days | Peta | bar: WEEK 2 T to WEEK 2 W
1.6 | Create contracts and statements of work for vendors |  |  |  | 3 days | Peta | bar: WEEK 2 R to WEEK 3 M
2 | Milestone 2: Receive the tablets and Test them
2.1 | Wait for tablets to arrive | Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems -has to ship from further away warehouse, adds a few days |  |  | 10 days | Peta | bar: WEEK 4 M to WEEK 5 F
2.2 | Reorder any broken tablets |  |  |  | 1 day | Peta | bar: WEEK 6 M
2.3 | Make sure tablets compatible with current POS software | depends on if we have 3.0 or older, I think ours might be older |  |  | 4 days | Deanna , seydou | bar: WEEK 6 M to WEEK 6 W
2.4 | Meet with staff on incoming tablet sytem and any features that might affect tipping and payment |  |  |  | 1 hour | Deanna | bar: WEEK 6 T
2.5 | Decide on and mock upmenu items to promote on system and link coupons | still waiting, Carter unpredicatble |  |  | 1 week | Carter | bar: WEEK 4 M to WEEK 5 T
2.6 | Schedule both smaller and larger training sessions |  |  |  | 4 hours | Peta | bar: WEEK 5 W
2.7 | Work with Tablet vendor on custom branding, design, and uploading menus to tablets | vendor has done this many times, received estimate from mult. team members |  |  | 4 hours | Seydou |  | WEEK 3 T: 0
2.8 | Install Cross-promotional feature on tablets that pair menu items and add-ons | never done before, try and work with vendor or Seydou |  |  | 2 days | Peta | bar: WEEK 6 R to WEEK 6 F
3 | Milestone 3: Train Management and staff
3.1 | Test tablets working and that staff has credentials to access | do day of pre-training |  |  | 4 hours | Peta | bar: WEEK 8 T
3.2 | Pre-training meeting to introduce tablets and changes to staff before training them on the tablets | low risk as just presenting tablets and plan (each training on dif day) |  |  | 1 hour | Peta | bar: WEEK 8 T
3.3 | Small training of PjM, GMs, and Dir. of Ops on tablets by Seydou | never done before, but used to trainings |  |  | 4 hours | Seydou | bar: WEEK 8 W
3.4 | Larger trainign of FOH and BOH workers on tablets by GMs, PjM | never done before |  |  | 4 hours | Alex | bar: WEEK 8 R
4 | Milestone 4: Install tablets and ready for launch
4.1 | Create troubleshoot/support plan for launch day |  |  |  | 4 days | Peta | bar: WEEK 10 M to WEEK 10 R
4.2 | Install tablets at bars in Downtown and North Area locations (wiring) | needs 2 half days at each location to minimize business impact |  |  | 3 days | Peta | bar: WEEK 10 F to WEEK 11 W
4.3 | Test run tablet system in with friends and family |  |  |  | 4 hours | Deanna | bar: WEEK 11 R
4.4 | Implement Customer satisfaction survey on tablets |  |  |  | 1 day | Deanna | bar: WEEK 11 F
4.5 | Launch day |  | April 29th (F) | April 29th (F) | 1 day | Peta | bar: WEEK 12 F
4.6 | Upgrade tablets to newer system (swa out plugs) | simple, only delay is if tablets arirve broken or unforseen power outage |  |  | 1 day | Deanna

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone 1: Tablet and vendors selected
Research data points on tablet systems and enhancement
Gather historical data on booking process
Align and evaluate stakeholders
Calculate projections and enhancements
Interview members of the staff
Create project charter (scope and goals)
Schedule kick off meeting
Milestone 2: Tablet and vendors selected
Research tablet system options |  | 1 day
Connect Suace & Spoon with terrific Tablets for branding |  | 4 hours
Generate quotes and review costs for tablets and electrician vendors |  | 4 hours
Test out tablet systems |  | 3 days
Choose a tablet system and order tablets |  | 2 days
Create contracts and statements of work for vendors |  | 3 days
Milestone 3: Tablets working with proper features
Wait for tablets to arrive | Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems -has to ship from further away warehouse, adds a few days | 10 days | 1 week | 11 days | 3 weeks | H
Reorder any broken tablets |  | 1 day
Make sure tablets compatible with current POS software(upgrade) | depends on if we have 3.0 or older, I think ours might be older | 3 days | 4 hours | 3 days | 4 days | L
Meet with staff on incoming tablet sytem and any features that might affect tipping and payment |  | 1 hour
Decide on and mock upmenu items to promote on system and link coupons | still waiting, Carter unpredicatble | 1 week | 5 days | 1 week | 2 weeks | L
Schedule both smaller and larger training sessions |  | 4 hours
Work with Tablet vendor on custom branding, design, and uploading menus to tablets | vendor has done this many times, received estimate from mult. team members | 4 hours | 2 hours | 4 hours | 2 days | H
Install Cross-promotional feature on tablets that pair menu items and add-ons | never done before, try and work with vendor or Seydou | 2 days | 1 day | 2 days | 3 days | L
Milestone 4: Staff trained on tablet system
Test tablets working and that staff has credentials to access | do day of pre-training | 4 hours | 2 hours | 4 hours | 1 day | M
Pre-training meeting to introduce tablets and changes to staff before training them on the tablets | low risk as just presenting tablets and plan (each training on dif day) | 1 hour | 30 minutes | 1 hour | 3 hours | H
Small training of PjM, GMs, and Dir. of Ops on tablets by Seydou | never done before, but used to trainings | 4 hours | 3 hours | 4 hours | 6 hours | M
Larger trainign of FOH and BOH workers on tablets by GMs, PjM | never done before | 4 hours | 3 hours | 4 hours | 6 hours | L
Milestone 5: Tablets installed and ready for launch
Create troubleshoot/support plan for launch day |  | 4 days
Install tablets at bars in Downtown and North Area locations (wiring) | needs 2 half days at each location to minimize business impact | 4 days | 2 days | 4 days | 6 days | M
Test run tablet system in with friends and family |  | 4 hours
Implement Customer satisfaction survey on tablets |  | 1 day
Upgrade tablets to newer system (swa out plugs) | simple, only delay is if tablets arirve broken or unforseen power outage | 2 hours | 1 hour | 2 hours | 2 days | H

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators
Customer Satisfaction | Average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | Are the customers having a better dining experience with the tablets? | The average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees.
Customer Satisfaction | A one-minute or less average checkout time. | Are the tablets saving time? | Checkout time for guests is 1 minute or less.
Customer Satisfaction | Less than 5% of customers who use tablets report technical issues each week. | Do the tablets work as expected? | Less than 5% of customers who use tbalets report technical issues each week.
Customer Satisfaction | 98% tablet order accuracy. | Are the customers receiving the correct orders? | 98% of customers receive the correct order.
Customer Satisfaction | Less than 10 minute average wait time for seating.

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | Are the customers having a better dining experience with the tablets? | The average ticket time is 8 minutes for appetizers and 12-15 minutes for entrees. | How long did your entire dining experience take? Please use your best judegement. | Multiple choice | Less than 30 minutes | Between 30 and 45 minutes | Between 45 minutes to 1 hour | Between 1 hour and 1.5 hours | More than 1.5 hours
A one-minute or less average checkout time. | Are the tablets saving time? | Checkout time for guests is 1 minute or less. | How easy was the tablet for you to use? | Multiple choice | Extremely Difficult | Difficult | Nuetral | Easy | Extremely easy
Less than 5% of customers who use tbalets report technical issues each week. | Do the tablets work as expected? | Less than 5% of customers who use tablets report technical issues each week. | Did everyone in your party receive the correct order? | Yes/No | Yes | No
98% tablet order accuracy. | Are the customers receiving the correct orders? | 98% of customers receive the correct order. | How long did you wait between ordering your entree and it's arrival. Please use your best judgement. | Multiple choice | Less than 5 minutes | Between 5 and 10 minutes | Between 10 and 15 minutes | More than 15 minutes | Our order never arrived. We had to ask someone.
Less than 10 minute average wait time for seating. |  |  | How long did you wait in the lobby before being seated? | Multiple choice | 5 minutes or less | Between 5 and 10 minutes | Between 10 and 30 minutes | more than 30 minutes | I had a reservation
|  |  | Did you order any of the reccomended paired items? | Yes/No | Yes | No
|  |  | Were there any errors that occured during your dining experience? | Multiple choice | 0 errors | 1 error | 2 errors | 3 errors | 4 or more errors
|  |  | Would you reccomend dining here with the tablet experience to friends? | Yes/No | Yes | No
|  |  | Are there any other comments you have for us related to the tablet experience? If so, please let us know! | Open-ended | Open-ended
|  |  | Please rank the features of the tablet that you like from highest (1) to lowest (5). | Scaled | pairing eccomendations | the menu page | the checkout page (where you order and pay) | the games page | the featured items page
|  |  | Your checkout was quick and easy. | True/False | TRUE | FALSE

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
7 Digital Menu Ordering System Highlights To Keep Customers Coming Back For More | https://www.talech.com/blog/2020/11/06/resources-7-digital-menu-ordering-system-highlights-to-keep-customers-coming-back/ | 2021-10-07 | talks about autmatic pairing suggestions, something to consider
Best Uses for Tablets at Your Restaurant | https://www.business.com/articles/best-tablet-uses-restaurants/ | 2021-10-07 | talks about benefits of tablets for people with disbilities and anxiety, interesting! also talks about corss-promoting (inventory mix increase wanted) and how tablets can manage business inventory
Possible Tasks for launching a tabletop tablet restaurant project. | https://www.linkedin.com/pulse/possible-tasks-launching-tabletop-tablet-restaurant-project-irodinjo/ | 26-06-2023 | talks about the important tasks for launching a tabletop tablet restaurant project
utm_source=google&utm_medium=paid_search&gad_source=1&gclid=Cj0KCQjwkdO0BhDxARIsANkNcre6Y3pBi-3UtDhtxSbBpCpDyXlCMONPgipGzdC8KZ64u4312iyNnGMaAktxEALw_wcB